## Slide 1
ENGINEERING KICKOFF
Cekat Automations
Replacing embedded n8n with an in-house workflow engine and builder
Week 1 — Monday, August 3, 2026
Ben · Product

## Slide 2
WHY NOW
n8n is the wrong long-term foundation
Self-hosted, so it's cheap today. That's exactly what makes it fragile.
Licensing exposure is latent, not current
The Sustainable Use License doesn't contemplate hosting n8n so customers build workflows inside a product they pay for. Regularizing it means OEM pricing — per execution, pooled across every customer.
Operational fragility
We provision by writing directly into n8n's private database schema. Every upgrade risks breaking client automations — so in practice, we don't upgrade.
Workflows are quietly broken
We audited 4 live workflows from one client. Every single one had a defect a domain-aware tool would have prevented.
Full detail: Decision Brief · PRD Section 1
CEKAT AUTOMATIONS
2
Notes: n8n is self-hosted by us, not on n8n Cloud — no per-execution fee today. That's the whole point: cheap now because we bent the rules on how it's provisioned, expensive the day we regularize it. OEM licensing is per-execution, pooled across every customer, and n8n's own guidance says white-labelling isn't available. Full argument: Decision Brief, and PRD Section 1.2.

## Slide 3
THE EVIDENCE
These aren't careless mistakes
They're what n8n's design allows. Mechanism, not mood.
4/4
audited workflows had a defect
Source: “Label New,” “Social Media Tracker,” “Voucher bayar di klinik” — one client, audited in depth.
A stray “x” in an expression silently killed the Hot Leads label branch
Two nodes wrote to the wrong CRM board — a copy-pasted UUID
TikTok leads never got a CRM record — the “open” branch wired to nothing
A label match used exact-equals against a value with a trailing space — dropped silently
1 of 28 identical timestamp writes missing timezone conversion — landed 7 hours off
Free-text IDs, optional fallback branches, per-node timezone handling, copy-paste as the only way to scale.
CEKAT AUTOMATIONS
3
Notes: All four workflows are one client (Euromedicagroup) — a heavy user, not necessarily representative. That's exactly why the census (this week) matters: we don't yet know if this defect rate holds across the client base. If it does, it's the strongest argument in the whole pitch. PRD Section 1.2c and Appendix A have full workflow-by-workflow detail.

## Slide 4
THE PITCH IN ONE PICTURE
One workflow, before and after
TODAY — N8N
136
nodes in “Label New”
8,600 lines. One 4-node chain, copy-pasted 34 times across 6 inboxes.
CEKAT AUTOMATIONS
~12
nodes, same behavior
One multi-inbox trigger, one CRM lookup, one router, six updates.
The reduction scales with how much duplication a client has — dramatic for heavy users, modest for someone running three simple workflows.
CEKAT AUTOMATIONS
4
Notes: This is the slide to slow down on. The 12-node rebuild uses a multi-inbox trigger, a lookup table to resolve the board per inbox, and a mandatory fallback branch on the router — the three primitives in the next slide. Full worked example with the actual node list: PRD Appendix B.

## Slide 5
HOW WE THINK ABOUT IT
Four ideas carry the whole product
Familiar by default
Match n8n wherever we have no reason to differ. Clients have months of muscle memory — every gratuitous divergence is a support ticket.
Typed references, not free text
Boards, inboxes, and labels are pickers backed by live IDs, validated on save and publish. The wrong-board bug becomes unrepresentable.
One automation, many scopes
A trigger subscribes to N inboxes at once. 136 nodes collapses to about 12.
Nothing fails silently
Routers require a fallback branch or they won't publish. Every run is logged and attributable to a node.
CEKAT AUTOMATIONS
5

## Slide 6
SCOPE
Narrower than n8n. Deeper on Cekat's data.
No 500 connectors. No arbitrary code execution.
Every action maps to a /business_workflows/* route we already run in production.
This is an orchestration layer over APIs that already exist — plus a canvas. We are not building 30 integrations.
TRIGGER
→
LOGIC / DATA
→
ACTION
Every node declares a category (engine behavior) and a domain (where you find it in the palette).
Conversation
CRM
Marketing
Flow
Utility
CEKAT AUTOMATIONS
6

## Slide 7
UNDER THE HOOD
Reuses infrastructure we already run
Cekat domain events
webhook · label · CRM write · cron
→
Automation Dispatcher
scope filter
→
Queue
BullMQ / Redis
→
Automation Worker
executes the graph
Scope filtering happens before enqueue — an inbox we don't watch never creates a run.
Fire-and-forget: an automation failure never blocks conversation ingestion.
↓
Cekat APIs
CRM
CDP · Datadog
CEKAT AUTOMATIONS
7
Notes: Reuses BullMQ/Redis and Supabase/Postgres — no new runtime to operate. Scope filtering before enqueue is the direct fix for n8n's cost shape: an inbox we don't watch never creates a run. Loop-heavy batch runs (Sync Data Book New style) need their own wall-clock limits and checkpointing — see PRD Section 5.3 and 7.5 on retention design, built to avoid n8n's execution-table bloat failure mode.

## Slide 8
HOW WE SPLIT THE WORK
Three streams, one manifest contract
Engine
Executor, expressions, dispatcher, retries, run persistence. Self-contained and deep — the fastest way to learn Cekat's event flow.
Adapters & API
Trigger, action, and CRM adapters plus the REST surface. Best onboarding path: each adapter is small, shippable, and teaches one part of the platform.
Builder
Canvas, config drawer, test run, live execution view. Parallel from week 1 against a frozen manifest schema.
A new node type = one manifest + one handler. No engine changes, no frontend changes.
CEKAT AUTOMATIONS
8

## Slide 9
THE PLAN
Eight weeks to Milestone 1
PHASE 0
Week 1
Foundations
Manifest schema
Data model
Full workflow census
Key spikes
PHASE 1
Weeks 2–5
Engine, API-first
Working engine, no UI yet
Shippable on its own
PHASE 2
Weeks 4–8
Builder
Canvas, node config
Test run, live executions
MILESTONE 1
PHASE 3
Weeks 9–14
Hardening
RBAC, credentials
Migration tooling
First 3 clients
FULL RELEASE
Phase 1 delivers value without the canvas — if the builder slips, we still have a working engine.
CEKAT AUTOMATIONS
9
Notes: Treat Phase 1 scope as provisional until the Phase 0 census lands — that's an explicit gate, not a formality. If the census surfaces a workflow shape we haven't planned for (like the batch-sync discovery did), Phase 1 gets re-scoped before it starts, not after. Full plan with ticket-level breakdown: PRD Section 12.

## Slide 10
STARTING MONDAY
What you're doing this week
Engine
Node manifest schema + JSON Schema validator
Data model migrations — automations, versions, triggers, runs, steps, lookup tables
Run-context & expression evaluator design doc
Adapters & API
n8n workflow census — script export across ALL clients, not just one
Spike: CRM change-event source — does a hook exist, or do we need an outbox table?
Manually audit 2–3 workflows from other clients
Builder
Spike: React Flow — node rendering, ports, custom edges
Spike: live-execution push channel (SSE + Redis pub/sub)
Review the manifest schema draft against real config needs
Exit criteria: manifest frozen · migrations merged · CRM trigger source decided · census delivered — before Phase 1 scope locks.
CEKAT AUTOMATIONS
10

## Slide 11
WHAT'S STILL OPEN
Five things being decided this week
Do segment/CDP triggers ship in v1, or v2?
Most time-critical — changes what Adapters builds this week.
How do we honor “every Cekat function should be callable”?
Proposal: everything reachable via HTTP + our Open API; ~20 most-used get first-class nodes.
Where does the CRM-field-changed event come from?
This week's spike — a real unknown, not a formality.
Legal read on the current n8n arrangement
Sets urgency. Doesn't block Monday.
Design handoff with Nic
Wireframe or hi-fi — enough to anchor engineering context.
None of this blocks Monday. Phase 0 is designed to survive these moving.
CEKAT AUTOMATIONS
11
Notes: Item 1 is the one to watch — the CEO's own notes list segment/CDP triggers first, and this plan has them in v2. Could genuinely go either way; the mitigation is designing the trigger registry so they're drop-in adapters regardless of when they ship. Full CEO-requirements trace: PRD Appendix C. Decisions 1-7 with recommendations: Decision Brief.

## Slide 12
WHAT WE'RE AIMING FOR
90 days after full release
60%
of n8n clients migrated
<1%
of runs fail — 100% visible in-app
<30s
for CS to answer “did this run?” — no n8n login
0
n8n executions across migrated clients
“The launch narrative, per migrated client: we moved your workflow over and fixed the bugs you didn't know you had.”
CEKAT AUTOMATIONS
12

## Slide 13
WHERE TO GO FOR MORE
Two documents, three people
Decision Brief
The why — licensing, cost, the ask. 8-minute read.
PRD — Cekat Automations
The how — full spec. Has a reader map at the top; use it, don't read it linearly.
Supporting: n8n — Features & Capabilities · Segmentation PRD (shared condition model) · MRKT Automation RFC
Ben
Product & scope
Nic
Technical & design alignment
CS
Census & client migration
CEKAT AUTOMATIONS
13

## Slide 14
Let's build the tool that makes n8n unnecessary.
Full context is in the PRD. Questions go to Ben.
Monday, August 3, 2026 — Cekat Automations